## Projects
ProjectID | ProjectName | ProjectDescription | ProjectStartDate | ProjectEndDate | ProjectStatus | ProjectManagerID | Budget
1 | River Bank Protection | Protecting river banks using concrete walls | 2024-01-10 | 2024-06-15 | In Progress | PM001 | 500000
2 | Water Pipeline Installation | Laying a new pipeline network for water distribution | 2024-02-05 | 2024-08-30 | Not Started | PM002 | 1200000
3 | Water Treatment Plant Setup | Setting up a new plant to treat water from River X | 2024-03-20 | 2024-12-31 | In Progress | PM003 | 2500000
4 | Groundwater Recharge System | Developing a system for groundwater recharge near urban areas | 2024-02-15 | 2024-05-20 | Completed | PM004 | 800000
5 | Sewage Treatment Facility Upgrade | Upgrading the existing sewage treatment facilities | 2024-04-01 | 2024-09-15 | In Progress | PM005 | 1800000
6 | Lake Restoration | Restoration of Lake Y with sediment removal and aeration | 2024-01-20 | 2024-06-30 | In Progress | PM006 | 950000
7 | Urban Water Conservation Program | Implementation of water-saving measures in the city | 2024-03-05 | 2024-10-30 | In Progress | PM007 | 750000
8 | Dam Safety Assessment | Assessing the safety and integrity of Dam Z | 2024-05-01 | 2024-07-20 | Not Started | PM008 | 600000
9 | Storm Water Management | Developing stormwater management systems in flood-prone areas | 2024-03-15 | 2024-08-15 | In Progress | PM009 | 1100000
10 | Rural Drinking Water Supply | Installing drinking water supply systems in rural villages | 2024-04-10 | 2024-12-15 | Not Started | PM010 | 2000000
11 | Desalination Plant Installation | Building a desalination plant to provide potable water | 2024-06-01 | 2025-03-01 | Not Started | PM011 | 3500000
12 | River Cleaning Campaign | Cleaning and de-silting of River K | 2024-03-25 | 2024-09-01 | In Progress | PM012 | 300000
13 | Water Quality Monitoring Network | Setting up a monitoring network for water quality parameters | 2024-05-15 | 2024-12-10 | Not Started | PM013 | 850000
14 | Water Meter Installation | Installing smart water meters for households in city P | 2024-02-20 | 2024-09-30 | In Progress | PM014 | 500000
15 | Reservoir Expansion | Expanding the capacity of Reservoir T | 2024-04-05 | 2024-11-15 | Not Started | PM015 | 900000
16 | Floodplain Reforestation | Planting trees in flood-prone areas to reduce soil erosion | 2024-03-12 | 2024-07-25 | In Progress | PM016 | 400000
17 | Coastal Erosion Control | Implementing measures to prevent coastal erosion near Village Q | 2024-02-10 | 2024-11-10 | In Progress | PM017 | 700000
18 | Hydropower Feasibility Study | Conducting a feasibility study for a new hydropower plant | 2024-01-25 | 2024-05-25 | Completed | PM018 | 300000
19 | Water Reuse System | Designing and constructing a water reuse system for industries | 2024-04-15 | 2024-12-30 | Not Started | PM019 | 1500000
20 | Water Awareness Campaign | Promoting water conservation practices among citizens | 2024-03-01 | 2024-05-01 | Completed | PM020 | 100000

## Tasks
TaskID | ProjectID | TaskName | TaskDescription | TaskStartDate | TaskEndDate | TaskStatus | AssigneeID | EstimatedHours | ActualHours
1 | 1 | Digging Foundations | Excavating the ground for foundation construction | 2024-01-15 | 2024-01-30 | Completed | EMP001 | 100 | 110
2 | 1 | Laying Concrete Walls | Constructing concrete walls along the river bank | 2024-02-01 | 2024-05-15 | In Progress | EMP002 | 300 | 120
3 | 2 | Site Preparation | Clearing the area for pipeline installation | 2024-02-10 | 2024-02-28 | Not Started | EMP003 | 80 | 0
4 | 2 | Laying 100 ft Pipe | Installing a 100 ft water pipeline segment | 2024-03-01 | 2024-03-10 | Not Started | EMP004 | 50 | 0
5 | 3 | Equipment Procurement | Acquiring necessary equipment for the water treatment plant | 2024-03-25 | 2024-04-10 | In Progress | EMP005 | 100 | 30
6 | 4 | Planning and Design | Creating designs and plans for groundwater recharge system | 2024-02-20 | 2024-03-10 | Completed | EMP006 | 50 | 60
7 | 4 | Construction Supervision | Overseeing construction of recharge pits | 2024-03-15 | 2024-05-05 | Completed | EMP007 | 200 | 190
8 | 5 | Facility Inspection | Inspecting existing facilities to identify upgrade needs | 2024-04-05 | 2024-04-20 | Completed | EMP008 | 40 | 45
9 | 6 | Sediment Removal | Removing sediment from Lake Y | 2024-01-25 | 2024-03-30 | In Progress | EMP009 | 150 | 100
10 | 7 | Public Awareness Campaign | Conducting workshops and events to promote water conservation | 2024-03-10 | 2024-04-20 | Completed | EMP010 | 60 | 70
11 | 8 | Dam Structural Analysis | Analyzing structural integrity of Dam Z | 2024-05-05 | 2024-06-15 | Not Started | EMP011 | 120 | 0
12 | 9 | Stormwater Channel Design | Designing channels for effective stormwater flow | 2024-03-20 | 2024-05-10 | In Progress | EMP012 | 180 | 80
13 | 10 | Survey and Mapping | Conducting surveys and mapping areas for water supply systems | 2024-04-15 | 2024-05-05 | In Progress | EMP013 | 70 | 20
14 | 11 | Plant Design | Designing the layout for the desalination plant | 2024-06-10 | 2024-07-20 | Not Started | EMP014 | 100 | 0
15 | 12 | River Cleaning Phase 1 | Removing debris and waste from River K | 2024-03-28 | 2024-04-15 | In Progress | EMP015 | 80 | 30
16 | 13 | Sensor Installation | Installing water quality sensors across the network | 2024-05-20 | 2024-06-30 | Not Started | EMP016 | 150 | 0
17 | 14 | Meter Installation Phase 1 | Installing smart meters in zone 1 | 2024-02-25 | 2024-04-05 | In Progress | EMP017 | 100 | 40
18 | 15 | Reservoir Wall Reinforcement | Reinforcing the walls of Reservoir T | 2024-04-20 | 2024-05-30 | Not Started | EMP018 | 90 | 0
19 | 16 | Reforestation Preparation | Preparing the soil for planting in flood-prone areas | 2024-03-18 | 2024-04-10 | Completed | EMP019 | 40 | 50
20 | 17 | Coastal Barrier Installation | Installing barriers to prevent coastal erosion | 2024-02-15 | 2024-04-30 | In Progress | EMP020 | 200 | 150

## Milestones
MilestoneID | TaskID | MilestoneName | MilestoneDescription | MilestoneDueDate | MilestoneStatus
1 | 1 | Site Survey Completed | Complete the survey of the digging site | 2024-01-20 | Completed
2 | 1 | Equipment Mobilization | Bring necessary equipment to the site | 2024-01-22 | Completed
3 | 1 | Digging Completion | Complete excavation of foundation areas | 2024-01-30 | Completed
4 | 2 | Material Delivery | Delivery of all required materials to the site | 2024-02-05 | In Progress
5 | 2 | First Wall Segment | Construct the first segment of the concrete wall | 2024-03-01 | In Progress
6 | 2 | Midpoint Inspection | Inspection of the wall segments constructed so far | 2024-04-01 | Not Started
7 | 2 | Wall Completion | Completion of all concrete wall segments | 2024-05-15 | Not Started
8 | 3 | Site Preparation Start | Clear vegetation and debris from the pipeline installation area | 2024-02-12 | Not Started
9 | 3 | Earthwork Activities | Conduct earthwork and leveling for the pipeline installation | 2024-02-20 | Not Started
10 | 3 | Site Preparation End | Finalize site preparation for laying the pipeline | 2024-02-28 | Not Started
11 | 4 | Pipeline Material Check | Ensure the availability of 100 ft pipe material | 2024-03-03 | Not Started
12 | 4 | Pipe Installation Start | Begin laying the 100 ft water pipeline | 2024-03-05 | Not Started
13 | 4 | Pipe Jointing Completion | Complete the jointing of pipeline segments | 2024-03-08 | Not Started
14 | 4 | Pressure Test | Conduct pressure test to ensure pipeline integrity | 2024-03-10 | Not Started
15 | 5 | Supplier Contract Finalized | Finalize contracts with suppliers for equipment procurement | 2024-03-28 | Completed
16 | 5 | First Batch Received | Receive the first batch of equipment for the water treatment plant | 2024-04-03 | In Progress
17 | 5 | Quality Check | Conduct quality checks on received equipment | 2024-04-05 | In Progress
18 | 5 | Equipment Installation Start | Start installing equipment at the water treatment plant | 2024-04-15 | Not Started
19 | 6 | Design Submission | Submit groundwater recharge system design to authorities | 2024-02-25 | Completed
20 | 6 | Design Approval | Approval of design plans for groundwater recharge system | 2024-02-28 | Completed
21 | 7 | Construction Team Mobilized | Mobilize the construction team to the site | 2024-03-10 | Completed
22 | 7 | Excavation for Recharge Pits | Begin excavation for groundwater recharge pits | 2024-03-20 | Completed
23 | 7 | Mid-Project Review | Review project progress at the halfway mark | 2024-04-15 | Completed
24 | 7 | Pit Construction Completion | Complete the construction of recharge pits | 2024-05-05 | Completed
25 | 8 | Facility Inspection Start | Begin inspection of existing sewage treatment facilities | 2024-04-07 | Completed
26 | 8 | Damage Assessment | Assess damages and defects in existing facilities | 2024-04-12 | Completed
27 | 8 | Inspection Report Submission | Submit the facility inspection report | 2024-04-20 | Completed
28 | 9 | Sediment Analysis | Analyze the type and volume of sediment in Lake Y | 2024-01-28 | Completed
29 | 9 | Dredging Preparation | Prepare dredging equipment and team for sediment removal | 2024-02-05 | Completed
30 | 9 | Sediment Removal Halfway | Remove 50% of the sediment from Lake Y | 2024-02-28 | In Progress
31 | 9 | Full Sediment Removal | Complete the sediment removal from Lake Y | 2024-03-30 | In Progress
32 | 10 | Campaign Strategy Meeting | Conduct meeting to strategize public awareness campaign | 2024-03-10 | Completed
33 | 10 | Campaign Material Development | Develop materials for the public awareness campaign | 2024-03-15 | Completed
34 | 10 | Launch Awareness Campaign | Launch the public awareness campaign | 2024-03-18 | Completed
35 | 10 | Campaign Completion | Conclude the campaign activities | 2024-04-20 | Completed
36 | 11 | Data Collection Preparation | Prepare data collection methods and tools for structural analysis | 2024-05-08 | Not Started
37 | 11 | Analysis Kickoff | Begin structural analysis of Dam Z | 2024-05-10 | Not Started
38 | 11 | Interim Analysis Report | Submit an interim report on dam safety | 2024-06-05 | Not Started
39 | 11 | Final Analysis Report | Submit the final analysis report | 2024-07-15 | Not Started
40 | 12 | Preliminary Design Review | Review initial designs for stormwater management channels | 2024-03-25 | Completed
41 | 12 | Channel Excavation Start | Start excavating stormwater management channels | 2024-04-05 | In Progress
42 | 12 | Midway Excavation Check | Conduct a midway check on excavation progress | 2024-04-25 | In Progress
43 | 12 | Channel Design Completion | Complete the design of stormwater channels | 2024-05-05 | In Progress
44 | 13 | Survey Team Mobilization | Mobilize survey team for mapping areas | 2024-04-20 | In Progress
45 | 13 | Initial Survey Completion | Complete initial surveys for water supply areas | 2024-04-28 | In Progress
46 | 13 | Mapping Finalization | Finalize mapping for rural water supply areas | 2024-05-01 | In Progress
47 | 13 | Reporting | Submit final mapping report | 2024-05-05 | In Progress
48 | 14 | Plant Site Evaluation | Evaluate the site for desalination plant construction | 2024-06-15 | Not Started
49 | 14 | Plan Approval | Obtain approval for the desalination plant layout | 2024-07-10 | Not Started
50 | 14 | Design Finalization | Finalize the design of the desalination plant | 2024-07-15 | Not Started